## INFO
MICRO-CREDENTIAL PROJECT CHARTER TEMPLATE
This template was developed by Dave Cormier (2022), digital learning specialist at the University of Windsor, and is part of A Micro-Credential Toolkit for B.C. (Prud'homme-Généreux, A., 2023).
CC BY NC SA
To access the template, select the green Project Charter tab below.
Cormier provides the following instructions:
Micro-credential overview section
The overview section defines the micro-credential’s Goals and Objectives. While there are distinctions between these two terms, goals are more conceptual. They speak to the strategy or value that the micro-credential will bring. Objectives are observable changes. They are measurable. One reason to include both goals and objectives is that some people on the team will respond better to aspirational language while others will respond better to concrete language. Articulating both will address all team members’ preferences.
The Program Description field can serve as common language for the team when talking about the micro-credential with external people. They can simply copy the description and paste it in an email.
The Desired End State serves to identify when the project objectives are met and the project wraps up. There is always the risk of scope creep and/or of the work continuing beyond the intended scope. Having this indicator allows the team to recognize when the intended project is finished, and to determine whether to close the project and move on to the next one or turn it over to the people who will maintain and operate the program as part of regular operations.
Scope section
The role of this section is to protect against scope creep. In any project, there are always opportunities to do more than initially intended. However, if these are pursued, the project may never get done, or not done in a timely manner. This section keeps the team and decision-makers focused.
The Out of Scope section can also serve as a “parking lot” where excellent ideas are noted for future projects.
Risks section
This section allows a team to identify potential risks to the timeline or the completion of the project.
The Likelihood of each identified risk is given a score from 1 to 4, with 1 representing an event that is very unlikely to occur, and 4 an event that is very likely to occur. A similar scale is applied to the Impact column, with 1 an event that will have minimal effect on the team’s ability to complete the project as planned, and 4 an event that causes significant disruption.
In a risk management matrix, the score given to the likelihood of an event happening is multiplied by the score given to the impact of that event. This score can help to prioritize which mitigation strategy to put into place, with the higher scored risks given greater priority.
Critical members of the group will have helpful input for this section. And by having a mitigation strategy in place, the group can adopt a positive, solutions-focused mindset.

## Project Charter
Micro-credential Project Charter
Micro-credential Name
Date Created |  | Faculty Lead
Admin Lead |  | Project Contact
Other Contacts |  | Version #
Target Start Date |  | Target End Date
Estimated Funding Required |  | Funding Source
Micro-credential Overview
Goals | (How will offering this micro-credential improve the current situation for learners, employers, or other stakeholders?)
Objectives | (What measurable changes will happen?)
Program Description | (How would this project be explained to a person not involved in it?)
Employer Connection | (Define the depth of integration with employers and name them.)
Desired End State | (How do we know this project is over?)
Deliverables
Deliverables |  | Responsible Person |  | Due Date
Scope
In Scope |  | Out of Scope
Roles
Name | Role |  |  | Time Required
Project sponsor
Team lead
Risks
Risk | Likelihood of Occurrence (1 to 4) | Impact if it Occurs (1 to 4) | Priority | Mitigation
0
0
0
0
0
Project Approval
Approved By
Links to Other Documents